## Slide 1: Jamuna Multipurpose Bridge Bangladesh, 1972 – 1998 GENG5505 Project Management and Engineering Practice Group 6 – Wednesday 2pm

## Slide 2
This section provides an overview of the Jamuna Bridge in Bangladesh as well as related management issues and recommendations mentioned in this report
SECTION A
PROJECT BACKGROUND

## Slide 3: Shehab Section

## Slide 4: Ravanjot Section

## Slide 5
This section will analyse in detail the management issues related to Jamuna Bridge in Bangladesh
SECTION B
PROJECT ANALYSIS

## Slide 6: Eden Section

## Slide 7: Ye Section

## Slide 8: Issues in Execution Stage and Finalization Stage of the Jamuna Bridge
Ye li 24427082
-Construction challenges​
-Supply and management of resources
-Management of structural maintenance of bridges
-Environmental and social impacts​

## Slide 9: Construction Challenges
Ye li 24427082
- Challenges due to changing river morphology
- Impact of special climatic conditions
- Need to build complex structures (guide dams, rockfall berms, etc.)
Execution stage
Image Source: [https://www.slideshare.net/slideshow/foundation-of-jamuna-bridge-method-construction/265917512#15]

## Slide 10: Supply and Management of Resources
Ye li 24427082
- Difficulties in transporting materials and equipment (sea transport limitations, climate impact)
- Labor shortages and training needs
Execution stage
Image Source: [26,041 Jamuna Bridge Stock Photos, High-Res Pictures, and Images - Getty Images | Jk bridge]

## Slide 11: Management of Structural Maintenance of Bridges
Ye li 24427082
- Cracks in bridge structures (causes and management)
- Importance of maintenance management
Finalization stage
Image Source: [(PDF) Cracks in the box girders of Bongobondhu Jamuna Multipurpose Bridge- Identification of causes based on FE analysis (researchgate.net)]

## Slide 12: Environmental and Social Impacts
Ye li 24427082
- Impact on local ecosystems and biodiversity
- Socioeconomic impacts (unemployment, relocation, changes in education and health services)
Finalization stage
Image Source: [Jamuna Multipurpose Bridge | Huckbody Environmental Ltd]

## Slide 13
This section will address the issues identified in Section B of the Jamuna Bridge project in Bangladesh and provide management recommendations
SECTION C
RECOMMENDATION

## Slide 14: Zhulin Section

## Slide 15
SECTION C
RISK MANAGEMENT
Resettlement the Char people
River regulation works
Polluting the local environment
Managing the workforce
Quality of construction
Risk Event

## Slide 16: 5 by 5 priority grid
Risk Event | Probability | Impact | Priority | Responsibility | Strategy | Review
1. Resettlement the Char people | Certain | Very High | 25 | Very High | Action Now | Weekly
2. River regulation works | Certain | High | 20 | Moderation | Plan Action | Monthly
3. Quality of construction | Likely | High | 12 | Moderation | Plan Action | Monthly
4. Managing the workforce | Unlikely | Moderation | 6 | High | Plan Action | Monthly
5. Polluting the local environment | Likely | Moderation | 9 | Moderation | Do Nothing | Half Year
Risk Registers
SECTION C
RISK MANAGEMENT

## Slide 17
Risk-Response Matrix
Notes: A systematic risk register was used to track these risks, prioritizing them using a 5x5 grid of probability and impac

## Slide 18
SECTION C
RISK MANAGEMENT
Establishing an Inspection Panel: This panel would be responsible for identifying and addressing the needs and placement of the Char people at the processing of the project
Holding Regular Risk Review Meetings: This proactive approach ensures that identified risks are effectively managed and that new risks are promptly addressed, preventing major disruptions to the project.
Other Risk Management
Safety risk
Environmental Risks
Regulatory and Legal Risk
Project Management Risk
Managing Conflict Risks of Interests

## Slide 19
SECTION C
SKATEHODER MANAGEMENT
Local Political Leaders
Financial Institutions (the World Bank)
General Public
Suppliers/Subcontractors
Government Authorities
Project Sponsor
Environmental NGOs
Char People
Media
Stakeholder Power and Interests Matrix

## Slide 20
PARIS Framework
SECTION C
SKATEHODER MANAGEMENT
S
A
I
P
Approve: The Project sponsor or executives should be responsible for approving key aspects such as budget approvals and critical milestones, ensuring that the Project aligns with organisational goals.
Signoff: The roles of stakeholders who will provide final acceptance and sign-off on the Project's key deliverables should be clearly defined. This ensures that the results of each major phase are formally acknowledged, with a client representative signing off on the final acceptance document upon Project completion.
Inform: The Project clients and external stakeholders should receive regular progress reports to keep them informed of the Project's status and any changes that may impact them.
Participate: During the project planning phase, the project manager and team members should be designated as participants responsible for developing the project plan.
R
Responsible: The Project manager should be responsible for communicating with the Char people, ensuring that their resettlement is carried out according to the plan, and
addressing any concerns that may arise during the process.

## Slide 21
SECTION C
SKATEHODER MANAGEMENT
Procurement Management System
This system would provide effective control over people of the supply chain, ensuring that accountability is
maintained throughout the Project. By tracking the source and usage of materials, the Project team can make sure the responsibility is placed on the person or the team.
Information Management System
Placement Personnel Database
This system would compile and record detailed information on all affected residents, allowing the Project team to develop fair and transparent compensation and resettlement plans. The system should also track the progress of resettlement activities, ensuring that all commitments are fulfilled and that any issues are promptly addressed. This approach not only helps to mitigate social risks but also fosters trust and cooperation between the Project team and the affected communities.

## Slide 22: Dylan Section